3.1.1.1 Risk Identification Template

Overview

Risks are assumptions taken for granted. By identifying underlying assumptions, we will be able to identify potential risks. Our focus is on identifying risks associated with projects.

Step 1: Defining Success Criteria for a Work Package.

| [No.]Work Package(WP) | Success Criteria(SC)[No.] |
| --- | --- |
| <<1.1.1WP label>> | SC1: …………………………….. |
|  | SC2: ……………………………. |
|  | SC3: ……………………………. |

Step 2: Evaluate each success criteria against the following questions

SC1:

Q1) What factors are necessary to ensure this success criteria?

List of Success conditions/assumptions (avoid listing resource related success factors as resources are separately evaluated in (Q3))

Q2) What condition would cause these assumptions to fail?

List of Failure conditions

Q3) What resources are necessary to ensure the success of these conditions?

R1_Resource Label; Availability confidence [high ¦ medium ¦ low]; Capability confidence [high ¦ medium ¦ low]; Risk Level.

|  | Take Note While identifying success and failure conditions, be sure to consider dependencies or interfaces between work packages and how that can affect successful completion of the work package. Dependencies can take the following forms: - Sequential dependency WP B requires WP A to finish. - Information dependency WP B needs information/data from WP A. - Resource dependency WP B needs the same person/equipment/budget being used by WP A. - Quality dependency WP B assumes that the output of WP A meets a particular quality standard. - External dependency WP B depends upon a regulator, vendor, government agency, client, etc. - Decision dependency WP B cannot proceed until somebody makes a decision. - Interface dependency Two work packages have to integrate their outputs correctly. For (Q3) consider the following categories of resources: People; Skills, expertise, availability. Money; Budget, cash flow. Technology; Software, hardware, systems. Information; Data, reports, permissions. Knowledge; Expertise, institutional knowledge. Access/Authority; Approvals, permissions, stakeholder access. |
| --- | --- |

Example::

| [No.]Work Package(WP) | Success Criteria(SC)[No.] |
| --- | --- |
| 1.1.1 Conduct stakeholder review | SC1: Stakeholders are available. |
|  | SC2: Interviewers are competent. |
|  | SC3: Interview questions are appropriate. |
|  | SC4: Stakeholders provide honest responses. |

SC1: Stakeholders are available.

Q1) What factors are necessary to ensure this success criteria?

No.; Factor necessary for stakeholder availability; Certainty level; Risk level. 1; The relevant stakeholders have been identified and their roles are known.; High; Low. 2; Stakeholders see sufficient value or obligation to participate in the review.; Medium; Medium. 3; Stakeholders know that a interview is scheduled, its purpose, date, format and expectations.; Medium; Medium. 4; A common time can be agreed upon, particularly where multiple stakeholders are involved.; Low; High. 5; Stakeholders receive the documents/data/materials necessary to participate meaningfully.; Very High; Very Low. 6; Participation is not merely confirmed; stakeholders remain engaged for the required duration.; Medium; Medium. 7; Travel restrictions, emergencies, institutional disruptions, connectivity problems, etc. do not prevent participation.; Very High; Very Low. 8; The review remains sufficiently important compared with other stakeholder commitments.; High; Low.

Q2) What condition would cause these assumptions to fail?

Necessary condition; Assumption; Condition that could cause the assumption to fail; Risk level. Stakeholders are correctly identified; We have identified all relevant stakeholders; A stakeholder is overlooked or a new stakeholder becomes relevant; Very low. Stakeholders are willing to participate; Stakeholders will be willing to participate; Stakeholder sees no value, has competing priorities, or is dissatisfied with the project; Medium. Stakeholders receive timely information; Invitations/contact details will reach stakeholders; Contact information is outdated, invitation is missed, or communication channel fails; Low. A mutually suitable time can be established; A common time can be found; Stakeholders have incompatible schedules; Medium. Listed above are factors that are beyond the control of the organization i.e. stakeholder related factors primarily because the organization is confident that activities on their side can be successfully addressed.

Q3) What resources are necessary to ensure the success of these conditions?

Resource; Availability confidence; Capability confidence; Risk Level. R1_Stakeholder database/contact list; High; High; Very low. R2_Stakeholder contact persons/coordinators; High; High; Very low. R3_Stakeholder time/calendar information; Medium; High; Low. R4_Project coordinator/review coordinator; High; High; Very low. R5_Communication channels (email, phone, messaging); High; High; Very low. R6_Internet/network connectivity; Medium; High; Low. R7_Audio-visual equipment; High; High; Very low. R8_Review agenda and schedule; High; High; Very low. R9_Backup stakeholder/authorized representative; Low; Medium; Medium. R10_Contingency communication channel; High; High; Very low.